## 01.22.2018
XSL Project Advances
2018-01-22 | AGENT |  |  |  | Morning Team time: From 9:05 to 10:35
| Lennon | Erick | Gabriel | Josias
Notes | Navbar creation. Navbar tabs. Navbar style. Setting default tab. | CSS Style changes | CSS Review
| Tabbed panel completion. Fields reorganized. Added Step Section. | Main Page segment to: Master Container>Header>LeftContainerLeftNavbarLeftValuesContainer>RightContainerRightNavbarRightValuesContainer>Footer | Paging Buttons added.
| Added variables and and counters for the corresponding tab. | MasterContainer width: 1200px / height: 1500px
| Added css for the tabbed panel. | Changing back to wrapper , width: 1350px;
| Classes "jarinfobox1" and "jarinfobox2" created to add css to the textboxes | adding functions for scope
| Modified variables fields | countjarnamespaces
| Setting proper structure per each tab content | countheaders
countdefaults
countvariables
countfields
Adding functions to tab -> JarInfo Namespaces Headers Defaults Variables Fields
Adding Title on top of values "Step1 Step 2 .. "
Adding Normalized variables for all fab5 (This is a must)
We made a division of variables ( General variables - Extra variables )

## 01.23.2018
XSL Project Advances
2018-01-23 | AGENT
| Lennon | Erick | Gabriel | Josias
Notes | OOF | A - Standard Template was added to the new interface XSL.
Fields and variables were bind to the template
We are now able to generate the values from each field/variable to the template in real time
JAR Info field was activated and bind to the template
Variables bind to the fields already.

## 01.24.2018
XSL Project Advances
2018-01-24 | AGENT
| Lennon | Erick | Gabriel | Josias
Notes | added combo boxes for locations and namespaces
added "add" and "remove" fields buttons for defaults, variables and fields
separate the variables into 3 sections: general, location and extra
changed the namespaces tab to settings tab
settings tab using namespaces, for each delimiter and tag filter
array modified using the new characters
added code for the textbox

## 01.25.2018
XSL Project Advances
2018-01-25 | AGENT
| Lennon | Erick | Gabriel | Josias
Notes | Configure code to add extra variables and removing variables by pressing the buttons
Adding combo boxes to set templates
Separate fields, variable and defaults to add code
Xpath copy setups
Location functions
Namespaces functions modified
Modified switch cases to make replacements in the code
Added option to automatically fulfill the variables